## Sheet1
SEVERITY
| Risk | Result of risk | known problems | Likelihood | Impact | Risk Level | mitigation | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Lack of project understanding | turn in a non functiong project | Lack of technical understandind of the multi-tired architecture | 4 | 5 | 20 | Read ims projec and QA community notes | 2 | 4 | 8 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | internet issues | submit unfinished project | miss out on project working time | 1 | 5 | 5 | Have everything backed up | 3 | 5 | 15 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | mismeasure time | Not organizing time | working harder and causing stress to try and finish | 3 | 5 | 15 | Set goals each day and execute | 4 | 5 | 20 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | loosing data | computer hard drive crash | Project work tha was completed get's erased | 1 | 5 | 5 | make sure everything backed up | 1 | 5 | 5 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | [11 empty] | Unlikely | 1 | 2 | 3 | 4 | 5
6